## Sheet1
Task # | Task Name | Task Notes | Task Owner | Effort (hours) | Start (date) | Finish (date) | Dependencies | Task Status
Team Charter
1 | Schedule team kickoff meeting |  | Mike | 1 | 2021-01-25 | 2021-01-25 |  | Completed
2 | Brainstorm Team Charter sections |  | Mike | 2 | 2021-01-28 | 2021-01-28 | 1 | Not Started
3 | Create Team Charter |  | Mike | 3 | 2021-01-29 | 2021-02-04 | 2 | Not Started
4 | Create Status Report & Lessons Learned Template |  | Mike | 1 | 2021-01-29 | 2021-02-04 | 2 | Not Started
5 | Review & Edit deliverables |  | Mike | 1 | 2021-02-05 | 2021-02-06 | 3, 4 | Not Started
6 | Submit Assignment to Canvas |  | Mike | 1 | 2021-02-07 | 2021-02-07 | 5 | Not Started
Enter Deliverable Here
7
8
Enter Deliverable Here
9
10
Enter Deliverable Here
11
12
**Resource Availability:
Mike | Monday - Friday (9-5PM), Saturday (12-3), Sunday (12-3)